## Hardware
Description | Start Week | End Week | Duration
HW/SW Planning Phase | 2019-09-16 | 2019-09-22 | 6
Design and test of clock division circuit for quavers/semi-quavers | 2019-09-22 | 2019-09-29 | 7
Gather required hardware | 2019-09-22 | 2019-09-29 | 7
Gather requirements and begin writing User Stories for software. | 2019-09-22 | 2019-09-27 | 5
Design of software structure. | 2019-09-30 | 2019-10-04 | 4
UI design for PC interface of software | 2019-09-30 | 2019-10-06 | 6
Design and test of circuit for outputting of relevant frequency waveforms to double integrator | 2019-09-30 | 2019-10-13 | 13
Implementation of hardware circuit using components designed in previous weeks for basic 60bpm tempo | 2019-09-30 | 2019-10-13 | 13
Software outputting relevant music file types with basic interface. | 2019-10-03 | 2019-10-13 | 10
Demonstration of hardware circuit prototype in week 4 on FPGA | 2019-10-14 | 2019-10-16 | 2
Demonstration of software outputting relevant music file types as designed in previous weeks | 2019-10-14 | 2019-10-16 | 2
Software connecting to and sending data to FPGA | 2019-10-14 | 2019-10-25 | 11
Design and test circuit for tempo changing hardware | 2019-10-14 | 2019-10-22 | 8
Interfacing with IR LED + remote control to control tempo changes | 2019-10-14 | 2019-10-25 | 11
Implementation of circuit containing components designed in previous weeks. | 2019-10-25 | 2019-11-03 | 9
Demonstration of hardware circuit prototype in week 6-7 on FPGA | 2019-11-03 | 2019-11-04 | 1
Demonstration of software sending data to and connecting with FPGA | 2019-11-03 | 2019-11-04 | 1
Any additional features or delays … TBD | 2019-11-04 | 2019-11-15 | 11

## Software
currently these aren't separated … for now