## Slide 1: Week 5 Project Updates
COMP 3601 - Libra
Presenter: Ki Fung Kelvin Ting

## Slide 2: Gantt Chart
Chart: 
| HW/SW Planning Phase | Design and test of clock division circuit for quavers/semi-quavers | Gather required hardware | Gather requirements and begin writing User Stories for software. | Design of software structure. | UI design for PC interface of software | Design and test of circuit for outputting of relevant frequency waveforms to double integrator | Implementation of hardware circuit using components designed in previous weeks for basic 60bpm tempo | Software outputting relevant music file types with basic interface. | Demonstration of hardware circuit prototype in week 4 on FPGA | Demonstration of software outputting relevant music file types as designed in previous weeks | Software connecting to and sending data to FPGA | Design and test circuit for tempo changing hardware | Interfacing with IR LED + remote control to control tempo changes | Implementation of circuit containing components designed in previous weeks. | Demonstration of hardware circuit prototype in week 6-7 on FPGA | Demonstration of software sending data to and connecting with FPGA | Any additional features or delays … TBD
Start Week | 43724 | 43730 | 43730 | 43730 | 43738 | 43738 | 43738 | 43738 | 43741 | 43752 | 43752 | 43752 | 43752 | 43752 | 43763 | 43772 | 43772 | 43773
Duration | 6 | 7 | 7 | 5 | 4 | 6 | 13 | 13 | 10 | 2 | 2 | 11 | 8 | 11 | 9 | 1 | 1 | 11

## Slide 3: Software Development Progress
(Staff)

## Slide 4: Software Development Progress
When pressing a key on the piano, it plays a sound
Use MIDI to play notes (useful for playback)
Multithreading (no need to wait on playing file)

## Slide 5: Software Development Progress
Next Progress:
  Ability to record songs and playback, such as “Record” button
  Modify the methods of loading and saving files, and undoing changes
Problems:
  One of our group members (Tingting) got sick so the progress is a little bit slow
  Wasting time to figure out how to import images (solved)
Notes: Build Action

## Slide 6: Hardware Development Progress
Finish debugging FPGA
Music can be played through the speaker in the required speed
Next progress:
  Building analogue, custom remote
Problems:
  Yet to purchase control components (IR LED, IR photodiode, Op-Amp, wire, etc.)
Notes: Initially: can’t play long music (repeating first note for some reason)
Everything works for tested case